## School Improvement Plan

2021-2023

At Talavera Junior School, all pupils, staff, and governors are committed to the continued journey of school improvement. As an Outstanding school, we are driven and committed to ensuring every child gets the best possible education.

Together with the support and contribution of all stakeholders, we have built on our growing success to determine the direction for further improvement. Our School Improvement Plan identifies areas for focus.

This School Improvement Plan unifies the vision of the school, the school’s self-evaluation, the achievements made in the last School Improvement Plan, an outstanding Ofsted inspection and the ambitions for 2021 – 2023. It takes into careful consideration the impact the pandemic has had upon learning, the curriculum, children’s well-being and the community. It carries forward key aims from 2019-2021 which were not completed.

The plan is implemented by the whole school and it must be continually monitored and reviewed by both school leadership and our governing body. Reports of progress and attainment are shared termly with the governing body to ensure our continued improvement.

This year, we are closing the gap in children’s learning through rigorous teaching and learning, immediate intervention and a skilfully-adapted curriculum.

Summary Review of School Improvement Plan 2021 – 2023

| RAISING ATTAINMENT AND MEETING NATIONAL EXPECTATION OR GREATER DEPTH |  |
| --- | --- |
| Key Priorities: Area 1: Raising Attainment and ensuring excellent progress Objective 1 – Close the gap for attainment across core subjects through Outstanding teaching and learning. Immediate intervention embedded to close the gap. Objective 2 – Curriculum adaptation where needed (ensuring all subjects have outstanding teaching sequence and units). Objective 3 – Parent involvement in raising attainment. | Evidence of Outcomes: -100 % of teaching is good or better; 70% of teaching Outstanding across all subjects. - Attainment across Lower Key Stage 2, in all subjects is at least 75% national expectation; 20% Greater Depth in writing, reading and maths. - 15 RWM % Greater Depth. - 70 RWM % national expectation - 100% of pupils make at least good progress. Majority making accelerated progress - Attainment across Upper Key Stage 2, in all subjects is at least 80% national expectation; at least 20% Greater Depth in writing, reading and maths. - 20RWM % Greater Depth. - 75RWM % national expectation - 100% of pupils make at least good progress. Majority making accelerated progress INDIVIDUAL CLASS TARGETS TO BE SET OCTOBER PHASE 1 |
| OUR LEADERSHIP CULTURE |  |
| Area 2: Our Leadership Culture - To develop leaders across the whole school in the classroom, through middle leaders and the strategic leadership team. - To maintain and develop our CPD programme for all staff to meet our needs and vision with consideration of the ‘catch up’ curriculum. - To maintain and adapt our strategic leadership of core subjects to close the gap to expected | EXPECTED OUTCOME - An inspiring strategic team is developed which leads the school forward from our Outstanding judgement; leadership qualities are celebrated. - All staff are accountable for developing practice and improving teaching and learning. - All staff have autonomy for their development. - All subjects are strategically driven to close the gap to Expected from missed education during the pandemic. |
| COMMUNITY HUB |  |
| Area 3: Community Hub - To continue to create a safe and stimulating environment for all children to achieve and develop children’s confidence, resilience and voice through wider opportunities and challenges. - To maintain and further strengthen our relationships within our community, focusing on our parents and carers. - To develop our role as a CPD hub of our community. Focusing on sharing best practice across Hampshire. | EXPECTED OUTCOME - All children are safe at school and know how to safeguard themselves. - Children are more confident, resilient and ready to tackle challenges; they see their role in the community. - We maintain and further develop our role within the community. Parents are actively involved in all aspects of school life within the constraints of the current climate. - Talavera Junior School shares best practice and is a hub of the community and across Hampshire. |

Talavera Junior School Milestone Targets 2021 - 2023

| By December 2021 |  |  | By April 2022 |  |  |  |  |  | By July 2022 |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| High Expectations for All: 100% teaching observed to be Good or better. 50% teaching observed to be Outstanding. |  |  | High Expectations for All: 100% teaching observed to be Good or better. 70% teaching judged to be Outstanding. |  |  |  |  |  | High Expectations for All: 100% teaching observed to be Good or better. 70% teaching judged to be Outstanding. |  |  |  |
| Phase 1 at B D |  | Phase 2 B D S |  |  |  | Phase 3 B D S |  |  |  |  | Phase 4 B D S |  |
| AREA 1  IMPACT Achieved  Steps taken but IMPACT completed  Not achieved/ No IMPACT |  |  |  |  |  |  |  |  |  |  |  |  |
| Area 1: Raising Attainment and ensure excellent progress Objective 1 – Close the gap for attainment across core subjects through Outstanding teaching and learning. Objective 2 – Curriculum adaptation across all subjects (ensuring all subjects- Outstanding teaching sequence and units). Objective 3- intervention embedded to close the gap daily. Objective 4 – Parent involvement in raising attainment, with a focus on reading across Lower Key Stage 2 |  |  |  |  | EXPECTED OUTCOME: - Children close the gap to be back on track and reaching their potential. - Improved % of good and outstanding teaching. 100% good and 70% Outstanding across the school. - RWM 20% greater depth. - RWM 70% national expectation - 100% of pupils’ good progress. Majority making accelerated progress - INDIVIDUAL YEAR GROUP TARGETS TO BE SET OCTOBER PHASE 1. - Parents taking a greater role in raising attainment for their child/ children (particular focus on reading) |  |  |  |  |  |  |  |
| Objective 1 | Further raising attainment across core subjects |  |  | Success Criteria |  |  | Lead Person | Timescale |  | IMPACT |  | Evaluation- next actions /Gov. Monitoring |
| Strand 1 | All teachers’ subject knowledge is developed in-line with the curriculum for reading/writing and mathematics though CPD - with a focus upon ECTs plus new teachers and teachers in new year groups. |  |  | CPD Literacy Tree, Maths Specialist, Hampshire Training, consultants and PDMS. ECTs training |  |  | SLT/ SPECIALISTS | All Year |  | Subject knowledge secure all teachers |  |  |
| Strand 2 | Deputy Head, Head Teacher and subject leads to team teach and coach re teaching and learning to ensure quality and consistency of teaching and learning. All areas covering where needed. School focus shared writes. |  |  | Team teaching, ECT focus, attending planning meetings, support resourcing and coaching |  |  | LHB AW Subject Leads | Ongoing |  | Improve teaching and learning - % Outstanding |  |  |
| Strand 3 | High expectations of teaching and learning (monitoring/feedback/specific CPD) Good or better. Increase percentage of Outstanding teaching (focus core subjects and foundation). |  |  | Observations, book looks, learning walks, further CPD, feedback, coaching, TT |  |  | SLT | ALL YEAR |  | Increase % of children at national standard/Greater Depth |  |  |
| Stand 4 | Whole school focus throughout year of teaching and learning mental maths fluency being taught in mental starters (multiplication and division). |  |  | Mental Mathematics fluency PDMs and inset to develop T&L. Team teaching intervention. |  |  | PH AH LHB | ALL YEAR |  | Increase % of children at national standard /Greater Depth in mathematics |  | . |
| Stand 5 | Whole school focus throughout year of teaching and learning spelling. Spelling embedded through spelling wizards, the introduction of spelling seeds and shared writes. ALL spelling T and L to be at least Good with Outstanding elements or consistently Outstanding. Transition sessions and phonic element added to spelling wizards – embedded vocabulary. |  |  | Spelling PDMs and INSET day to develop T&L. Focus of monitoring and coaching and intervention. Team teaching. |  |  | HP AP | ALL YEAR |  | Increase % of children at national standard/Greater Depth in spelling. |  |  |
| Strand 6 | Further development of intervention strategies, which are robust, strategic and measurable impact is made. Immediate intervention daily and the focus. WHOLE FOCUS and monitored. |  |  | Review current practice, CPD for TAs, class teacher to shape re AFL. Immediate intervention embedded all year groups. |  |  | HT CL YEAR LEADERS | ALL YEAR |  | Increase % of children at national standard - children move from developing to secure. |  |  |
| Strand 7 | AfL to be used as the focus for all intervention. Focus teachers to use AfL as base for closing the gap for national standard. All PPA teachers same responsibility to signpost intervention. Early work in all classrooms focused and ensuring ‘catch up’ re core subjects. Completing any misconceptions from previous day. |  |  | Intervention impacts on progress linked to class learning. Intervention mainly in class. If out of class, different children, closing the gap. Year group leaders to oversee. |  |  | CT Year group leaders LSA | ALL YEAR |  | AFL at the centre of intervention. % children at National Standard increase 15% LKS2 Greater Depth 20% UKS2 Greater Depth |  |  |
| Strand 8 | Support staff teaching and learning strategies and subject knowledge further developed in-line with SIP. To ensure all intervention and split inputs are allowing accelerated progress. |  |  | LSA review of strengths, CPD given as a programme throughout the year and practice implemented |  |  | HT CL SLT | ALL YEAR |  | Improved intervention and class support |  |  |
| Strand 8 | Maintain focused marking with closing the gap, explanation and challenge across all subjects. Ensure all marking has response time and a dialogue in all subjects. Focus on SPaG and impact. Consistency with stickers and frequency in-line with the policy. Challenge set for GD opportunities that progress their learning |  |  | Closing the gap marking in all subjects Challenge marking in all subjects Dialogue evident in book looks - all children responding. Staff meeting autumn 1 re challenge GD |  |  | SLT YL CT | ALL YEAR |  | Feedback impacting on progress. Increase % of children at national standard/ greater depth |  |  |
| Strand 10 | Pupil progress meetings and class reports are further refined to ensure no negative trends or groups of children underachieving (Greater Depth focus). Assessment report for PP meetings streamlined and focus on impact- impact from catch-up provision closely monitored |  |  | SLT meetings – on agenda and year group meetings. Feedback used to develop further T and L. |  |  | SLT YL CT | Autumn 1 - On going |  | Talavera Assessment Model embedded and accurately assessing children. Impacting upon T and L No vulnerable groups |  |  |
| Strand 11 | Pupils with SEND are carefully and sensitively tracked in line with National Standard - consistently across the school and clear steps of progress evident. Most children tracked in-line with national standard. Additional immediate intervention, pre teaching and specific targeted programs embedded. |  |  | Tracker alongside whole school. Progress measure accurate. SEND report shows clear progress and attainment. |  |  | CL | On-going |  | SEN children tracked accurately and progress shown Children making Good progress. |  |  |
| Strand 12 | Greater Depth – all planning across reading writing and maths stretches children to their full potential with close tracking through class report. Provision is flexible and allows Greater Depth intervention. |  |  | Challenge for children across all subjects. GD staff meetings and drop-in workshops to support knowledge and provision |  |  | SLT YL CT | ALL YEAR |  | Increase % of Greater Depth writing and maths Further improved provision |  |  |
| Strand 14 | Service Premium – Ensure that Service Premium spending impacts upon service children settling into school quickly and making good to accelerated progress where needed. |  |  | SEE SP Spending FORM |  |  | HT YR CT | All YEAR |  | SP reaching national expectation and Greater Depth |  |  |
| Strand 15 | Pupil premium/ Catch-up premium – Ensure that all spending closes the gap so all disadvantaged children meet at least national expectation and make accelerated progress. Further analysis of SEN/ PP to ensure they are making good progress- embedding provision each phase. |  |  | SEE PP spending and provision form |  |  | HT YR CT | ALL YEAR |  | PP reaching national expectation and Greater Depth All at least good progress SEN PP making good progress |  |  |
| Strand 16 | To focus on RWM combined for Expected and Greater Depth through pupil progress/ intervention and data analysis (class reports) across upper KS2. |  |  | Teachers accurately predicting % RWM combined Intervention used to increase children achieving all 3 |  |  | AP CT | All YEAR |  | Greater number of children reaching RWM combined % in upper KS2 |  |  |
| Strand 17 | Greater Depth Lead to ensure all underperforming Greater Depth cohort meet Greater Depth though monitoring, support and additional provision- upper KS2 focus. Accurate GD across core subjects with consistency in benchmark. |  |  | Monitor vulnerable greater depth Intervention review PDM and book looks , sharing benchmarks |  |  | AP HT | ALL YEAR |  | All children at KS1 GD- GD at upper Key stage 2 Accurate assessment of GD beyond core subjects |  |  |
| Strand 18 | Strand 1 to 14 is further developed in Subject Quality Evaluation forms. Refer to SQE for all subjects and further detail |  |  | SQE forms |  |  | - | - |  | See impact sheets |  | See impact sheets |
| Objective 2 | Curriculum adaptation across all subjects (ensuring all subjects- Outstanding teaching sequence and units). |  |  | Success Criteria |  |  | Lead Person | Timescale |  | Impact |  | Evaluation- next actions / Gov. Monitoring |
| Strand 1 | Adaptation of all subjects (where needed) to cover content of missed curriculum from the pandemic. Careful consideration of timetabling and medium term planning to focus on ‘catching up’ and ‘closing the gap’ |  |  | Curriculum content covered previously missed learning. Medium term planning adapted Immediate intervention utilised ( additional hours of support) |  |  | SLT CT | Autumn – ongoing |  | Children taught all content for age-related expectation % of children closing the gap to Expected and reaching their potential |  |  |
| Strand 2 | Intervention carefully designed to ensure catch-up. Content closes the gap to the next concept and ensures all children are secure. Subject knowledge of professionals delivering intervention to be excellent. (as in attainment section above) |  |  | AfL used to design intervention and identify students LSA and teacher subject knowledge CPD outstanding |  |  | CT LSA SLT | Autumn – on going |  | Children taught all content for age-related expectation 100% of children closing the gap to Expected and reaching their potential |  |  |
| Strand 4 | Curriculum Development Team teach/ plan and coach teachers re curriculum and teaching and learning strategies. Focus good teachers, ECTs Subject leads and SLT to team teach |  |  | DH/HT to work with ECT and good teachers weekly. DH to support curriculum development with ECTs To team teach all subject leaders |  |  | HT DH Subject leaders | ALL YEAR |  | Improve teaching and learning. Increase good and outstanding teaching alongside curriculum development |  |  |
| Strand 5 | Maintain whole school handwriting and presentation expectation from Autumn 1- following weakness post-pandemic. Handwriting intervention Handwriting displays |  |  | All pen licences to be earned- new system of celebration – whole class Whole school approach and structure Increased provision whole class Additional intervention groups |  |  | HT AP/ HP YL CT | Autumn 1 – ongoing |  | Improved handwriting and presentation - whole school |  |  |
| Strand 8 | Develop creative writers – CPD and focus on embedding grammar into writing. Focus ECTs and new staff. Team teach English lead shared writing All writing – prewritten expectation piece for all teachers re consistency Creative writing opportunities added into early work |  |  | Literacy Tree consultants, PDMs and monitoring/feedback/team teaching. Models of writing standard |  |  | HP SN YL | Autumn Spring |  | Improve subject knowledge teaching strategies. Improved % of children at Expected and GD |  |  |
| Strand 9 – | Maintain a whole school reading culture embedded across the school. Whole school reading competition- reading culture all celebrated - each child and class. With a library focus, class readers and parent/carer reading link for Lower Key Stage 2 particularly Library increase interaction with outdoor library, suggest book displays and book reviews Reading projects developed- lunch time – HP Clear reading expectation in each class maintained. Parent expectation clear. Year leader to oversee. Children able to select and choose books for pleasure. Aldershot library to support and offer linked books |  |  | Children to complete challenge. Parents to engage with challenge. Wider range of books in class and school library. Children reading 3x a week at home. Children choosing a wide range of books. Children reading for pleasure |  |  | SLT CO CT LSA | Autumn 1- ALL YEAR |  | Improve reading provision. Increase % at national standard for Reading and GD children achieving their potential Whole school love of reading |  |  |
| Strand 11 | A whole school reading culture – whole school approach to reading with quality texts and clear teaching sequence. New medium term book planning embedded and updated with a wide range of genres and all carefully selected for age range Focus of improved fluency and pre teaching for SEN where applicable |  |  | Medium term plans accurate and up to date All new planning embedded Taught daily Excellent teaching sequences |  |  | HP/ AP YL CT | Autumn 1 |  | National Standard for Reading (75%) all year groups 20% greater depth |  |  |
| Strand 12 | Intervention development for children who are not at national standard for decoding and reading fluency – a non-negotiable bench mark set. LSA reading daily Phonics integrated into the curriculum where needed and training given. ( linked to attainment section above objectives) |  |  | Identified immediately Intervention embedded, impact monitored. Significant development with Salford reading scores |  |  | CL CO HP/ AH LSA | ALL YEAR |  | All children fluent readers by the end of year 3. Yr 4 – Marlborough |  |  |
| Strand 13 | Maths – subject knowledge development; maintain new staff and further reflection. ECTs. LSA subject knowledge development. AH – focus teaching program for support |  |  | Maths Specialist teacher - TT DH HT to TT external specialist Maths Hub training with PH |  |  | PH / AH DH HT | On going |  | Improved teaching and learning - % increased Outstanding. |  |  |
| Strand 14 | Maths - mental maths fluency develop throughout the school. Maths lead to develop through fast tracker and interventions. Also mental fluency overview embedded. Further development of mathematics intervention which is immediate, linked to the lesson - closing the gap for all children led by LSAs (within the sessions where possible/pm or early morning work). |  |  | Resources given. Expectation understood. Clear fluency LSA trained/ CPD Intervention remodelled. Invention labels throughout books |  |  | PH AH HT LSA CT | Autumn 1 on going |  | % of children at national standard increased. % of children at national standard increased. |  | . |
| Strand 16 | Maths- Maths Research Hub to maintain subject knowledge and share good practice with maths leads across Rushmoor and Surrey schools. PH to be maths subject lead for Surrey hub. AH starting subject specialism lead course. Each responsible for Outstanding maths provision within their year groups |  |  | Research group x8 across the year lesson observations and mastery discussion. 3x visits to subject knowledge course- PH X8 CPD days - AH |  |  | PH AH | Autumn 1 ongoing online |  | Improved teaching and learning and provision across own year group/ school and county. |  |  |
| Strand 18 | Maths lead to develop x fluency in year 4 so mean score of 20 in multiplication tests. Embedded into planning, implementation and intervention. X table checks throughout year 3/4/5 |  |  | Attend training Implement Impact measured Intervention |  |  | PH AH | ALL YEAR |  | % of children fluent re x increased across year 4 |  | . |
| Strand 19 | To ensure that the SEN and GD are appropriately challenged in all maths lesson and this is evident in their learning journeys (books) as mixed ability classes |  |  | Challenges evident GD children GD supported an stretched through CT / LSA SEN independent learning SEN task adapted for independence |  |  | CT Year Leaders PH AH | ALL YEAR |  | All children achieving their potential and independence of SEN |  |  |
| Strand 20 | All subjects - continual review and development of all subjects throughout the year – see SQE and impact sheets Any further concerns from the pandemic missed learning addressed |  |  | SQE Impacts sheets Book scrutiny Planning Assessment PP |  |  | ALL | ALL YEAR |  | See impact sheets |  |  |
| Strand 21 | All subjects – medium term plans reviewed and formatted in line with vision. All showing the progression through year groups and expectation. Clear, sequenced and building on prior learning – not completed last year. Any concerns across any unit addressed with year leader and subject leader. Year group overviews developed in line with new medium term planning. They must be uniform |  |  | Medium term planning sequenced and quality Consist across whole school Clear progression. Book scrutiny and learning walk. Subject leader additional workshops |  |  | ALL DH | ALL YEAR Autumn 1 |  | Quality planning across all foundation subjects Consistency across the subjects Progression evident. All units Outstanding Linked directly to medium term planning and showcase our curriculum. Consistency in format all year groups |  |  |
| Remote learning | All subjects are available online – 8 days of remote learning available per year group All core subjects are taught to a high standard Topic lessons are available to all pupils to ensure a full curriculum is delivered All lessons must be directly linked to the National Curriculum All children to have access to TT Rockstars and MyMaths homework as children in school do |  |  | Learning journeys are Outstanding Misconceptions are pre-considered in planning All children are able to access remote learning Technical difficulties are addressed at speed to avoid lost learning time Work is marked and a phone call home made weekly |  |  | Year leaders/ HT DHT | ALL YEAR |  | All pupils, regardless of time off school, make progress Learning time is not lost |  |  |
| Objective 3 | Parent Involvement in Raising Attainment |  |  | Success Criteria |  |  | Lead Person | Timescale |  | Impact |  | Evaluation- next actions / Gov. Monitoring |
| Strand 1 | Maintain communication with parent and carers re newsletters/ParentMail, curriculum maps and website communication. Maintain frequency and celebration of children’s learning through class assemblies, year group and upper and lower assemblies. Further develop Facebook media for events and communication. Continue to market through garrison magazine events and local press |  |  | More frequent newsletters, further ParentMail and website communication for parents. With a focus on celebrating learning and supporting learning. |  |  | HT LMD | On going |  | Communication with parent/carers improved. Celebrations of the school successes. |  |  |
| Strand 2 | Maintain expectation of parents support re reading and development of parent workshops throughout the year for children working below their potential following covid. Whole school and targeted children’s parents. 100% expected attendance for targeted parents (socially distanced). Year 3 parents meeting with a focus on reading catch up strategies from September. |  |  | Parent evening for all parents. Then targeted yr 3 4 and 5 reading groups for parents and children. 100% targeted parents attend. Quality texts shared and reading strategies |  |  | HT Year Leaders | Autumn 1 |  | Parent and school link further developed and % of children at National Standard for reading increased. Further close the gap linked to the content of the parent workshop to expected. |  |  |
| Strand 3 | Increased opportunities for parents to develop strategies for teaching and learning in mathematics linked to multiplication fluency. Focused packs for year 4 working below expectation. |  |  | Targeted workshops for mathematics and writing – key strands. Individual call to parents. |  |  | PH AH | Autumn 1 |  | Parent and school link further developed and % of children at National Standard for maths / x test increased. |  |  |
| Strand 4 | Parent/carer meetings to achieve 100% attendance and focused additional meetings when children are underperforming within each phase – possible phone /zoom. HT to call or write to any parent who doesn’t attend. |  |  | Teachers to target non-attenders and reschedule. Key resources given to parents to support their children in maths and writing. |  |  | HT CT | On going |  | Parent and school link further developed. Maintain high expectations. Particularly engaging new parents and carers |  |  |
| Strand 5 | HT or DH to meet with all new parents re learning and expectation to support when choosing the school. Parent partnership lead for cluster school accessed where needed for any early intervention. Parent support advisor sign posting Socially distanced when required |  |  | Parent welcome meeting. Progress updates. Use of parent partnership support. |  |  | HT SLT | On going |  | Parent and school link further developed and % of children at National Standard across all subjects |  |  |
| Strand 6 | Attendance welfare officer accessed across cluster of schools and expectation of 100% attendance. Support parents post C19. Celebration of 100% attendance termly. Education Welfare officer used to support parents where attendance under 93% EW plans embedded where required. DFE guidelines followed. |  |  | EW officer. Follow up any unauthorised attendance. EW plans in place Support for families. |  |  | HT LmD | On going |  | Improve attendance for improved attainment. Target 98%. No vulnerable groups. |  |  |

| AREA 2 |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Area 2: Our Leadership Culture - To develop leaders across the whole school in the classroom, through middle leaders and the strategic leadership team. - To maintain and develop our CPD programme for all staff to meet our needs and vision with consideration of the ‘catch up’ curriculum. - To maintain and adapt our strategic leadership of core subjects to close the gap to Expected. |  |  | EXPECTED OUTCOME - An inspiring strategic team is developed which leads the school forward from our outstanding judgement; leadership qualities are celebrated. - All staff are accountable for developing practice and improving teaching and learning. - All staff have autonomy for their development - All subjects are strategically driven to close the gap to expected |  |  |  |  |
|  | Our leadership Culture | Success Criteria |  | Lead Person | Timescale | IMPACT | Evaluation- next actions / Gov. Monitoring |
| Strand 1 | To direct our shared vision and SIP journey as a school that cascades into all aspects of the school. Ensuring ‘closing the gap’ message clear re lost learning due to the pandemic. Open SLT to whole school every half-term to discuss strategic next steps- whole school accountability. | Share vision Inset day. SIP created and edited by SLT. SIP shared with all stakeholders. Accessible, used and visible to all. Evaluate and adjust where needed on a half termly basis. Whole school impact review. |  | HT SLT GOV | Autumn 1 | Strategic vision and plan for the year embedded and revisited. Impact all children. |  |
| Strand 2 | Ensure that all year leaders have a clear understanding of the expectation of their role - to drive standards within their year group. With particular focuses on 75% reaching national expectation by the end of the year- phase 4 (lower KS2) and 80% above in upper KS2, closing the gap from the pandemic. | Coaching model - SLT members SLT meetings PDM PPA content DH to attend PPA |  | AW SLT | Autumn 1 – on going | All year groups make consistent and Good to Outstanding progress. Increase % of children at NS. |  |
| Strand 3 | Year group meetings every three weeks dedicated to supporting colleagues in raising standards and consistency ‘walking through learning books’ / sharing good practice. Consistency key across all classes. FOCUS CLOSING GAP/IMMEDIATE INTERVENTION | Focus on range of outcomes, quality outcomes, presentation and consistency across the year groups DH to attend PPA sessions |  | HT SLT YL | Every 3 weeks | Improve learning journeys in books consistently across a year group/then across school. |  |
| Strand 4 | SLT continued CPD to be experts in their subjects and ensure excellent leadership skills developed- focusing on their knowledge of progression re to C19 across core subjects. Subject courses attended and shared. PDM should be outstanding and engaging. An awareness of our staff expertise. | Maths Hub, moderators for Hampshire, cluster meetings, pyramid etc. – attend and cascade in SLT / PDM. Hampshire courses |  | SLT HT DH SLT CT LSA | On going | Strategic leaders who make an impact on teaching and learning beyond their classroom. Deliver excellent CPD through PDM |  |
| Strand 5 | Strategic monitoring system embedded where SLT are accountable for subject standards and year group standards. Impact of all subjects owned by leader and shared. Joint learning walk of books, remote learning and outcomes. Identification of next steps. | Monitoring cycle created and agreed as SLT linked to SLT placed on strategic assessment and monitoring calendar. Year leader accountability. |  | HT DT SLT | Autumn 1- on going | Improve % at national standard and consistency across year group/ whole school in core subjects. |  |
| Strand 6 | To develop professionals in their roles Strategic level Middle leaders Teachers LSA- greater accountability and training throughout the year Admin / caretaker Ensure all clear vision and making an impact. | Linked to PM Share SLT Embed Measure impact Coaching and support |  | SLT | Autumn Spring summer | Impact upon subject and T&L |  |
| Strand 7 | To maintain governors visits to support and challenge the school but linked to the key areas of the SIP and governors focus areas of responsibility – ownership of areas to support moving the school forward. Audits of key areas re safeguarding, Pupil premium and Service Premium. C19 catch up funding spending. Visits strategically throughout the year- linked to key points. | Create a strategic calendar where governor’s visits linked to key events linked to SIP/ area of focus. |  | HT SLT GOV | On going | Governors increased understanding of the SIP / focus areas. Further accountability. |  |
| Strand 10 | SQE which are focused and strategic for each subject (see individual forms). Middle leader coaching linked to their SQE plans and subject development with HT/DH. Termly review and coaching sessions. | Action plans reviewed Actions taken Impact measured Meeting HT/DH termly |  | HT/ DH | Autumn/ Spring/ summer | Clear impact upon T&L of subject and standards. |  |
| Strand 11 | Curriculum leads (including middle leaders) to take full ownership of progress and impacts the school regularly feeding back and supporting colleagues through team teaching. All units’ outstanding and prior learning built upon. Assessment progress further embedded –non core subjects. Medium term planning developed. Greater Depth stretched. SEN reaching full potential. | Action Plans Teaching good or better in all subjects TT opportunities identified, best practice shared. Clear and consistent assessment. |  | SLT subject Leaders | Autumn 1- On going | Actions embedded and % of children at National Standard in each subject increases 20% greater depth. |  |
| Strand 12 | Assessment standards and expectations further embedded –non core subjects. Consistency throughout year groups and across year groups. Greater Depth assessment standards outlined. | Action plans Assessment tracking Impact sheets PPA meetings SLT |  | SLT YR CT | ALL YEAR | All assessment embedded in very subject to support standards and expectations. |  |
| Strand 14 | Opportunities for all staff, teachers,ECTs, LSA, admin given opportunity to see best practice and share their practice. Coaching model used throughout the school. Informal and formal. | Head/ DH/AH / subject leads etc. dedicated TT weekly. |  | All staff | Autumn 1 Ongoing | Expertise shared and developed. |  |
| Strand 16 | LSAs given CPD every other week to have ownership of intervention, immediate intervention, split inputs so they can be exceptional and step into teaching where applicable. Knowledge and understanding developed in all subjects, all confident. LSAs observed by each other and other schools for best practice. | PM link intervention CPD split input Observations Subject knowledge development. Teaching opportunities and observations. |  | HT DH CL | Autumn 1 Ongoing | LSA making significant impact upon progress and attainment. |  |
| Strand 17 | CPD matrix shared with all staff lined to PM and expectation of embedding good practice/ CPD next steps. Investment and expectation shared. | PM reviews CPD matrix shared Impacted noted. |  | DH HT | ALL YEAR | Impact upon T&L and subject development/ subject knowledge. |  |

| AREA 3 |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Area 3: Community Hub - To continue to create a safe and stimulating environment for all children to achieve and develop children’s confidence, resilience and voice through wider opportunities and challenges. - To maintain and further strengthen our relationships within our community, focusing on our parents and carers. - To develop our role as a CPD hub of our community. Focusing on sharing best practice across Hampshire. |  |  | EXPECTED OUTCOME - All children are safe at school and know how to safeguard themselves. - Children are more confident, resilient and ready to tackle challenges; they see their role in the community. - We maintain and further develop our role within the community. Parents are actively involved in all aspects of school life within the constraints of the current climate. - Talavera Junior School shares best practice and is a hub of the community and across Hampshire. |  |  |  |  |
| Objective 1 | To create a safe and stimulating environment for children to achieve and develop children’s confidence, resilience and voice through wider opportunities and challenges | Success Criteria |  | Lead Person | Time scale | Impact | Evaluation- next actions / Gov. Monitoring |
| Strand 1 | All staff refreshed on safeguarding procedure/latest policies and their responsibility throughout the year – ensure ‘everybody responsible’ culture is created. All read ‘Keeping Safe/ child protection and safeguarding’ and whole school to receive training focusing on available services and current trends. All Hampshire learning and webinars accessed Regular Safeguarding updates through PDM. All safeguarding training recorded and updated. | Inset day – Hampshire complete Refresher New staff as induction |  | HT DH CL All staff | Autumn 1 | All staff safeguarding procedures Outstanding |  |
| Strand 2 | Mini safeguarding refreshers for staff 2x half termly – on safeguarding board- posters. Questionnaire and areas focused upon following audit of needs/ new legislation. | All staff confident regarding their safeguarding role. |  | HT DH CL | ALL YEAR | Outstanding safeguarding provision. |  |
| Strand 3 | To develop our core safeguarding team who are all trained designated lead who have a shared understanding and knowledge of safeguarding at Talavera Junior. Strategic oversite of all safeguarding. Governors safeguarding audit. Strategic team complete audit termly. | Inset day/ CPD Hampshire training/ Safeguarding team meeting weekly. Consistently review and audit areas of provision. |  | HT DH CL | Autumn 1- Ongoing | Robust safeguarding team |  |
| Strand 4 | To ensure all staff using CPOMS effectively and consistently –recording in line with expectation for safeguarding and behaviour. To ensure CPOMS is being used consistently for behaviour and analysed. Actions captured and behaviour analysed to reduce incidents each half term. | Inset day/ analysed/ further training where needed Behaviour analysis |  | HT DH | Autumn 1 | Online system for all safeguarding/ behaviour documents consistent. Number of behaviour incidents reduces. | . |
| Strand 5 | To raise awareness of cyber safeguarding issues for staff, parents and children through awareness slides in parent events/ further developed unit for all children – Computing unit 1 all year groups. All newsletters have a focus section for parents re apps/ issues and prevention ideas. Parent survey re their awareness and areas of need for their development and understanding. Completion of a whole school prejudice and discrimination unit in Autumn term. | PDM, Workshops, newsletters, whole staff training, new units in computing, questionnaire |  | LC HT | Autumn1 / Termly | Cyber safeguarding raised awareness across the school. Pupils aware of how to keep themselves safe. Reduced incidents. No racist incidents |  |
| Strand 6 | To maintain attendance across the school including persistent non attending families adopting the Hampshire Model working alongside Welfare Officer. Further reduce non-authorised absence through EWO. Reduce impact of poor attendance linked to the pandemic. Follow all guidance and recoding linked to the DFE | Embed Hampshire Model/ communication with parents/use action plans for parents/CPD office lead. Plan for persistent absence. Recoding in line with DfE |  | HT DT | Ongoing | Increase % of attendance reduce % unauthorised attendance AIM 98% |  |
| Strand 7 | Core values re launched for year 3 and 4 post pandemic lack of focus – school council to launch again and reinforced by all staff. All to ‘talk ‘core values. Core values weekly certificates embedded Talavera Treat reinstated linked to values Prefects leadership of values Embed the children’s roles across the school linked to their values: including prefects, student council, house captains, senior librarians, play leaders, perfects, energy monitors, green team . | Student council launch Teachers and LSA’s to reinforce. Assemblies focused Children using language and meaning. PSHE lessons linked. Talavera Treat Appoint/ train/ develop and review roles. Feedback through student council. |  | HT DH KS |  | Improved behaviour throughout the school year 3 and 4- and clear whole school vision Children ownership of their school. |  |
| Strand 7 | To maintain additional structured sports-based lunchtime provision alongside lunch clubs. Children to have ownership of lunchtimes through responsibilities, e.g. prefects, play leaders, Guinea pigs monitors. Lunch time lead to ensure ‘Healthy’ opportunities available and used including the Golden Mile/ structured games and trim trail. Camo Club, Young Carers club at lunchtime ‘ Lunch Bunch’ for focused play techniques | To sustain provision at lunch time. Review impact on feeling safe survey. |  | BW CHB NB LHB | Termly | Further improved behaviour at lunchtimes. Children have extended opportunities. Improve children’s fitness and health. |  |
| Strand 8 | To maintain our ‘Feeling Safe’ survey for children which can be evaluated and action taken where needed and implemented by student council to keep children feeling safe. To maintain Friendship Week (anti-bullying, cyber bullying) and Healthy Relationship Week are informative/embedded and impacts upon our children. | Survey Autumn 1 and Spring 2 actions taken and lead by school council. Feedback to governors/ stakeholders. Weeks embedded. All children participate. |  | Autumn 1 and spring 2 Autumn/ spring /summer | KS DH HT | Children feel safe in school- positive feedback survey – impact Spring 2. All children understand what bullying looks like and how to keep themselves safe. |  |
| Strand | To ensure sports premium is carefully spent to provide children with a range of rich and wide opportunities. The spending is carefully planned and reviewed for impact Any talented children provided with a range of opportunities. Identification of any talents. Additional sports training and team teaching ECTs and less confident. | See sports premium break down. |  | HT CH LF | Autumn 1- All year | Ensure all children have a wide range of sporting opportunities and any talents developed. Excellent provision and teaching of PE/ sports. |  |
| Strand 13 | To maintain and develop opportunities outside of the classroom for PSHE. Student council leading change. Weekly teaching of PSHE linked to our unique medium term planning for Talavera children’s needs and C19 impact. Mental health focus. | PSHE medium term plan. Children’s input. Wide range of opportunities added across the year. |  | HT KS | On going | All children have the opportunity to extended provision. |  |
| Strand 14 | To maintain ‘Healthy Schools’ provision through PSHE curriculum, school ethos and ‘Travel Plan’ initiative. Further development the strand of ‘mental health’ awareness and implementation for strategies for children and staff. Units adopted with a mental health focus and profession charities etc sign posted. Mental Health awareness week and units Staff support line available. | PSHE embedded into planning PDM developed SLT meetings P4C taught across the whole school Wellbeing taught throughout curriculum. |  | DH | On going | Further develop curriculum reflect children needs – children Keeping Heathly- Mental Health signposted |  |
| Strand 19 | To maintain my passport for Talavera. Ensure children settle immediately and begin to make progress immediately. | New program - LHB Train LSAs Analysis |  | CT LHB LSA MC | Ongoing | All children settle immediately. |  |
| Objective 2 | To maintain and strengthen our relationships within our community | Success Criteria |  | Lead Person | Timescale | Impact | Evaluation- next actions / Gov. Monitoring |
| Strand 2 | To ensure a whole school awareness of keeping well mentally – through the curriculum and wider provision. Well Being week will be for our whole community. Mental health t and l embedded throughout the whole PSHCE curriculum. Well-being lead for children and then staff (trained through well-being course). Issues added from pandemic. | Embedded in PSHE Bubble Time ELSA Camo Club Young Carer Club Mental health added further added into curriculum |  | LH AW ELSA | Autumn 2 ongoing | PSHE supports and raises awareness mental health Whole community Well being |  |
| Strand 3 | To ensure vulnerable families and deployed families are supported by our school. Improved my passport program with qualitative and quantitive outcomes | Initial interview Follow up programme Parent Partnership Camo club Purple stars ELSA Additional drop in sessions- SEN families |  | PP advisor SLT LSA CT CL | Autumn 1- on going | Families feel supported and access the provided provision Children settle quickly |  |
| Strand 5 | Parent workshops (see attainment), open afternoons, expectations sessions and open door policy for school. Adapted: - Online meetings - Telephone calls - Workshops in school - Meetings face to face | Workshops attended. Session and open afternoons attended. |  | YR CT HT LC | Autumn 1 – on going | Raising attainment for children Parents involved with learning. |  |
| Strand 6 | Cultural celebration days throughout the year celebrating our community and collective British values. Bristish values day, Nepali day, Fijian day and further cultural celebrations. | Cultural days. Parents to organise and resource. |  | HT DH SR | Termly | All cultures celebrated within our community. |  |
| Strand 8 POST C19 | Widen parent involvement/ wider audience again in person where possible. Maintain our further parent and children’s days. Dad’s camping, tag ruby competition with parents/ children. Mothers’ breakfast etc. | Events organised Parents attend Wide range of parents attend. Parents positive feedback |  | HT LMD DH CK | Termly | Events well attended and bringing the school community together again |  |
| Strand 9 | Autumn 2 onwards - Friends of Talavera set up and events supported by the group of parents such as summer fair, discos, cake sales and family linked days. SET UP AND ONLINE AUTUMN | Events supported. Parents advertising and leading. Range of well organised events. |  | Friends of Talavera HT | Autumn 2 – on going | Further funds raised for school. |  |
| Objective 4 | To develop our role as a CPD hub of our community | Success Criteria |  | Lead Person | Timescale | Impact | Evaluation- next actions / Gov. Monitoring |
| Strand 1 | To maintain and develop our Aldershot Hub – where best practice is shared and moderation across schools at CT and SLT level. Focus on moderation, core subject next steps etc Summer 1-Science, music and geography focus- development of subject from audit , subject knowledge, teaching, task design and review. | Aldershot Cluster working together. Moderation embedded across schools. Projects developed and working together re curriculum development. |  | HT SLT CT | On going – termly | Develop provision across all cluster – curriculum developed. |  |
| Strand 2 | To maintain and develop our relationship with the infant school to ensure excellent transition and the schools working collaboratively. To develop transition to secondary schools – Alderwood and Wavell. | Share good practice. Transition steps. Cross school teaching and moderation. Shared events. Shared SLTs. Regular cluster meetings. Transition clubs. Taster clubs. Sports links. |  | ALL SLT/ HT | On going – Autumn 1 | Smooth transition Shared good practice |  |
| Strand 3 | To lead our maths ECTs across Hampshire and Surrey. To develop their teaching and learning and their subject knowledge. HT to lead advocate for Hampshire Maths Hub | Lead CPD programme. Local cluster schools to attend. ECT’s to embed practice and share. Share best practice and share vision for Maths Hub. Market the school provision. |  | PH/ AH HT | Half termly | Improved subject knowledge and understanding for ECTs. School viewed as best practice. |  |
| Strand 4 | NCETM Maths Mastery Research – Talavera Lead. 2 x maths leads from each school to attend, mastery discussion, observe and share throughout the year. Phil- support Surrey and Hampshire schools outreach x3 days a half term. AH to begin Maths specialist training programme. | Hub set up. Schools attend. Team Teaching. Observations. Share and reflect. |  | PH AH | Autumn- ongoing | Maths Hub. Research Hub improving progress across school and cluster. |  |
| Strand 5 | Literacy Tree beacon school so share good practice and share writing journey with other schools. Continue to develop practice. | Literacy tree units. Outcomes. Share provision. |  | HP AP | Autumn ongoing | Share good practice for writing/ grammar/ spelling. |  |
| Strand 7 SOME REMOTE | To further develop other teachers through our English lead sharing - Spelling Hampshire CPD – lead session Further lead curriculum Hampshire courses- New head teachers course SEN Case study New headteacher mentor Service Pupil Rushmoor Lead Share classroom and leadership provision with other schools. | English Lead to share practice with Cluster schools. To continue being a moderator- sharing. Lead course Visitors from other schools to share good practice |  | HT DH HP/AP | Ongoing Autumn 1 | Improved writing provision throughout school and shared practice cluster. Share good practice Hampshire |  |